## Risks
RAID LOG — RISKS
DOCUMENT CONTROL
Project Name |  |  |  | Project Manager |  |  | Document ID | PMO-RAID-001 | Version | 1.0 | Last Updated
RISK SUMMARY
TOTAL RISKS |  | OPEN |  | CLOSED |  | ESCALATED |  | HIGH RATED |  | MEDIUM RATED |  | LOW RATED
6 |  | 5 |  | 1 |  | 0 |  | 3 |  | 2 |  | 1
Risk ID | Category | Risk Description | Trigger / Cause | Probability | Impact | Risk Rating | Mitigation Plan | Contingency Plan | Owner | Date Raised | Review Date | Status | Remarks
R-001 | Schedule | Resource availability during UAT phase may impact testing timeline | Key QA resource assigned to parallel project | MEDIUM | HIGH | HIGH | Confirm QA resource allocation with PM before Phase 4 begins. Request backup resource if needed. | Engage contract QA tester as backup if primary unavailable. | Project Coordinator | 05/02/25 | 05/03/25 | OPEN | Monitor weekly
R-002 | Technical | Data migration complexity may delay sign-off milestone | Legacy system data quality issues identified during extraction | MEDIUM | HIGH | HIGH | Conduct data profiling exercise in Phase 3 to identify and resolve data quality issues early. | Extend data migration dry run period by 3 days if issues persist. | Business Analyst | 05/02/25 | 21/02/25 | OPEN | Dry run in progress
R-003 | Technical | Integration between Portal and legacy system may fail during testing | Undocumented API dependencies in legacy system | LOW | HIGH | MEDIUM | Conduct API discovery session with legacy system vendor before integration testing begins. | Implement middleware workaround if direct integration is not feasible. | System Developer | 10/02/25 | 10/03/25 | OPEN
R-004 | Scope | Client may request additional dashboard features after BRS sign-off | Stakeholder alignment gaps during BRS sessions | MEDIUM | MEDIUM | MEDIUM | Conduct thorough requirements review during BRS. Obtain formal sign-off on scope boundary. | Raise formal Change Request if new requirements are introduced post BRS sign-off. | Project Coordinator | 16/01/25 | 22/01/25 | CLOSED | BRS signed off. Scope locked.
R-005 | Resource | Project Manager availability may be reduced during Go-Live phase | PM managing concurrent project in same period | LOW | MEDIUM | LOW | Agree PM availability schedule for Go-Live period in advance. Escalate to steering committee if conflict arises. | Delegate Go-Live coordination to Project Coordinator if PM unavailable. | Project Manager | 01/03/25 | 01/04/25 | OPEN
R-006 | Compliance | Government agency IT security requirements may delay deployment approval | Agency security review process not scoped into deployment timeline | MEDIUM | HIGH | HIGH | Engage agency IT security team during Phase 2 to obtain deployment approval requirements early. | Build 5-day buffer into deployment timeline for security clearance. | Project Coordinator | 16/01/25 | 07/03/25 | OPEN

## Assumptions
RAID LOG — ASSUMPTIONS
DOCUMENT CONTROL
Project Name |  |  |  | Project Manager |  |  | Document ID | PMO-RAID-001 | Last Updated
ASSUMPTION SUMMARY
TOTAL |  | VALIDATED |  | PENDING |  | INVALIDATED |  | CLOSED
6 |  | 3 |  | 3 |  | 0 |  | 0
Assumption ID | Category | Assumption Description | Basis / Rationale | Owner | Date Raised | Validated By | Validation Date | Status | Impact if Wrong | Remarks
A-001 | Resource | Project team resources will be available full-time throughout the project lifecycle | Confirmed verbally by PM during kick-off meeting | Project Manager | 02/01/25 | Project Sponsor | 08/01/25 | VALIDATED | Schedule delays and milestone slippage if resources are pulled to other projects | Confirmed at kick-off
A-002 | Technical | Legacy system APIs are documented and accessible for integration | Assumption based on vendor pre-sales technical discussion | System Developer | 02/01/25 |  |  | PENDING | Integration Phase 3 workstream may fail or be significantly delayed | Needs validation in Phase 2
A-003 | Client | Client will provide UAT participants within 2 working days of UAT plan distribution | Standard government ICT project practice | Project Coordinator | 02/01/25 | Client Representative | 22/01/25 | VALIDATED | UAT timeline will slip if client cannot mobilise participants on time | Confirmed in BRS sign-off meeting
A-004 | Environment | Test environment will be available and stable throughout Phase 3 and Phase 4 | Infrastructure provisioning confirmed in Phase 2 | System Developer | 05/02/25 |  |  | PENDING | Testing phases cannot proceed if environment is unavailable or unstable | Monitor during Phase 3
A-005 | Scope | No changes to approved BRS scope will be requested after sign-off | Client confirmed scope freeze at BRS sign-off meeting | Project Coordinator | 22/01/25 | Client Representative | 22/01/25 | VALIDATED | Budget and schedule overrun if scope changes are approved post sign-off | Change request process established
A-006 | Compliance | Government agency IT security approval will be obtained within 5 working days of submission | Based on previous project experience with same agency | Project Coordinator | 16/01/25 |  |  | PENDING | Go-Live deployment will be delayed if approval takes longer than estimated | Build buffer into deployment plan

## Issues
RAID LOG — ISSUES
DOCUMENT CONTROL
Project Name |  |  |  | Project Manager |  |  | Document ID | PMO-RAID-001 | Version | 1.0 | Last Updated
ISSUE SUMMARY
TOTAL |  | OPEN |  | RESOLVED |  | ESCALATED |  | CLOSED |  | HIGH PRI
5 |  | 2 |  | 0 |  | 1 |  | 2 |  | 3
Issue ID | Category | Issue Description | Impact | Priority | Raised By | Owner | Date Raised | Target Date | Actual Res. Date | Status | Resolution Action | Remarks
I-001 | Technical | Integration test environment setup delayed by 2 days | Phase 3 integration testing start date pushed from 10 Feb to 12 Feb | MEDIUM | System Developer | System Developer | 05/02/25 | 07/02/25 | 07/02/25 | CLOSED | Server provisioning completed. Environment ready by 7 Feb. | Resolved within tolerance
I-002 | Data | Legacy system data contains duplicate records affecting migration dry run | Data migration dry run results invalid. Sign-off milestone at risk. | HIGH | Business Analyst | Business Analyst | 19/02/25 | 21/02/25 |  | OPEN | Deduplication script being developed. Re-run scheduled for 22 Feb. | Escalate if not resolved by 22 Feb
I-003 | Client | Client UAT participants not confirmed 5 days before UAT start date | UAT may need to be delayed if participants are not available on time. | HIGH | Project Coordinator | Project Coordinator | 03/03/25 | 07/03/25 |  | OPEN | Follow-up email sent to client representative. Awaiting response. | Escalate to PM if no response by 05 Mar
I-004 | Process | Change request submitted by client for additional reporting dashboard feature | Scope and budget impact to be assessed. May affect Go-Live date. | HIGH | Project Coordinator | Project Manager | 10/02/25 | 17/02/25 |  | ESCALATED | CR raised and under review by PM and steering committee. | Steering committee decision pending
I-005 | Resource | QA Tester unavailable for 3 days during integration testing Phase 2 | Integration testing Phase 2 duration extended by 3 days. | MEDIUM | Project Coordinator | Project Coordinator | 19/02/25 | 27/02/25 | 27/02/25 | CLOSED | Contract QA resource engaged for 3 days to cover gap. | Resolved. No impact to milestone date

## Dependencies
RAID LOG — DEPENDENCIES
DOCUMENT CONTROL
Project Name |  |  |  | Project Manager |  |  | Document ID | PMO-RAID-001 | Last Updated
DEPENDENCY SUMMARY
TOTAL |  | OPEN |  | MET |  | AT RISK |  | BLOCKED
6 |  | 1 |  | 4 |  | 1 |  | 0
Dep. ID | Type | Dependency Description | Dependent On | Owner | External Party | Required By | Status | Impact if Late | Mitigation Action | Remarks
D-001 | External | Legacy system API documentation required before integration design can begin | Phase 3 Integration workstream — architecture design | System Developer | Legacy System Vendor | 10/02/25 | MET | Integration design cannot start without API documentation | Request documentation from vendor during Phase 2 planning | Received 8 Feb
D-002 | External | Government agency IT security approval required before Go-Live deployment | Phase 5 — Go-Live deployment milestone | Project Coordinator | Agency IT Security Team | 05/04/25 | OPEN | Go-Live cannot proceed without formal security clearance | Submit security review package 3 weeks before planned Go-Live date | Submission planned for 20 Mar
D-003 | Internal | BRS sign-off required before SRS drafting can commence | Phase 2 — SRS drafting task | Business Analyst | Client Representative | 22/01/25 | MET | SRS cannot be drafted without confirmed business requirements | Escalate to PM if BRS sign-off delayed beyond planned date | BRS signed off 22 Jan
D-004 | Internal | Master project schedule baseline required before Phase 3 can commence | Phase 3 — All development workstreams | Project Coordinator | Project Manager | 30/01/25 | MET | Phase 3 tasks have no confirmed dates without a baselined schedule | PM to approve baseline schedule by end of Phase 2 | Baseline approved 30 Jan
D-005 | External | Client UAT participants list and availability confirmation required before UAT plan distribution | Phase 4 — UAT plan preparation task | Project Coordinator | Client Representative | 03/03/25 | AT RISK | UAT plan cannot be finalised without knowing participant names and availability | Send formal request to client representative with 5 working day response deadline | Follow-up sent. No response yet.
D-006 | External | Server hardware delivery required before environment configuration can commence | Phase 3 — Workstream D environment configuration task | Project Coordinator | Hardware Vendor | 10/02/25 | MET | Environment configuration and testing cannot start without physical hardware | Confirm delivery schedule with vendor at least 2 weeks in advance | Delivered on time 5 Feb

## Instructions
HOW TO USE THIS RAID LOG
WHAT IS A RAID LOG
RAID stands for Risks, Assumptions, Issues, and Dependencies. It is a core PMO document used to track and manage the four key areas that can impact project delivery. Each category has its own sheet in this workbook. All four are updated regularly and reviewed in project status meetings.
RISKS SHEET
Log potential events that have not yet happened but could negatively impact the project. For each risk: assign an ID (R-001), describe the risk, identify the trigger, rate probability and impact (HIGH / MEDIUM / LOW), calculate the overall rating, document the mitigation plan, assign an owner, set a review date, and track status (OPEN / CLOSED / ESCALATED).
ASSUMPTIONS SHEET
Log statements accepted as true for planning purposes but not yet confirmed. For each assumption: assign an ID (A-001), describe the assumption, document the basis, assign an owner, track validation status (PENDING / VALIDATED / INVALID / CLOSED), and document the impact if the assumption turns out to be wrong.
ISSUES SHEET
Log problems that have already occurred and need resolution. For each issue: assign an ID (I-001), describe the issue, document the impact, set priority (HIGH / MEDIUM / LOW), assign an owner, set a target resolution date, track actual resolution date, and document the resolution action taken. Status: OPEN / RESOLVED / ESCALATED / CLOSED.
DEPENDENCIES SHEET
Log external or internal items your project depends on to proceed. For each dependency: assign an ID (D-001), describe what is needed, identify what project activity it blocks, name the external party if applicable, set a required-by date, and track status (OPEN / MET / AT RISK / BLOCKED).
RISK RATING MATRIX
Probability HIGH + Impact HIGH = Risk Rating HIGH. Probability HIGH + Impact MEDIUM = HIGH. Probability MEDIUM + Impact HIGH = HIGH. Probability MEDIUM + Impact MEDIUM = MEDIUM. Probability LOW + Impact HIGH = MEDIUM. Probability LOW + Impact MEDIUM = LOW. Probability LOW + Impact LOW = LOW. When in doubt escalate to MEDIUM.
REVIEW CADENCE
Review the full RAID log weekly as part of your project status cycle. Update statuses, add new items, and close resolved items. Do not delete closed or resolved items — they form your project audit trail. Escalated items must be reviewed with the Project Manager or Steering Committee within 2 working days.
DOCUMENT CONTROL
All four sheets share Document ID PMO-RAID-001. Update Version and Last Updated fields each time the log is revised. Classification is Confidential for most government ICT projects.